## Slide 1
Satellite Flight Operator Challenge Project
· Flight Operational Contact Plan · Algorithm · Python Automation
Anastasia Maria Giannakopoulou
· August 2026

## Slide 2
The Challenge
A 10-minute ground station contact · Part 1
1
Health Check
Verify telemetry: mode, power, thermal, AOCS, COMMS
2
Payload Downlink
Priority-1 mission data transfer
3
Platform Downlink
Priority-2 housekeeping data
4
COMMS Reconfiguration
New config applied via subsystem restart
Fixed parameters: 50 kbps up/down · RX permanently ON · TX commanded ON · full-duplex link

## Slide 3
Operational Design Principles
Guiding rules applied throughout the procedure · FOCP Section 8
1
Spacecraft safety first
A safe, understood state always outweighs completing the plan
2
Verify before proceeding
Confirm the expected result before starting the next dependent activity
3
Protect communications
COMMS restart only after configuration upload is verified and time allows
4
Protect contact time
Remaining time is reassessed before any retry or non-essential activity
5
Known end state
Spacecraft reaches LOS in a documented, verified configuration

## Slide 4
Time Budget – 10 Minute Contact
Table 7 - Proposed Contact-Time Allocation
1
2
3
4
5
6
7
8
1. Health Check
0:00–1:00 · 60s
2. Payload Downlink
1:00–5:00 · 240s
3. Platform Downlink
5:00–6:20 · 80s
4. Config Upload
6:20–6:50 · 30s
5. COMMS Restart
6:50–8:20 · 90s
6. TX Modulation
8:20–9:00 · 40s
7. Final Verification
9:00–9:40 · 40s
8. Contingency Margin
9:40–10:00 · 20s
Total: 600 s (10 min), 20 s contingency margin preserved for retries or additional verification

## Slide 5
Contact Procedure - Flow Logic
Sequential activities, each gated by a go / no-go decision
AOS - Contact Start
1. Initial Health Check
2. Payload Downlink (P1)
3. Platform Downlink (P2)
4. Configuration Upload
5. Restart COMMS Subsystem
6. Restore TX Modulation
7. Final Verification
LOS - Contact End
Recovery logic
Every activity is followed by a success check before the next step begins
On failure: verify link / status, then retry only if time and safety allow
If not recoverable: defer or abort the activity and protect the remaining plan
An unsafe spacecraft state ends non-essential ops and moves straight to End-of-Contact
Full annotated diagram - 7 decision points and Recoveries A;F - provided as a separate deliverable.

## Slide 6
Python Automation & Validation
A script that runs the same logic as the Contact Plan and flow diagram – Part 2
Tracks simulated contact time against the Table 7 budget
Applies the same go / no-go decision logic at every step
6 selectable failure scenarios exercise every recovery path
Retries only when time and safety allow, else defers or aborts
Produces an operator-style action / command / result log
SCENARIO = "normal" | "health_fail" | "payload_fail" | "platform_fail" | "config_fail" | "restart_fail" | "tx_fail"
Sample run “normal” scenario
Contact starts at AOS. TX_ON commanded.
STEP 1 - Health check: within expected conditions.
STEP 2 - Payload transfer: completed successfully.
STEP 3 - Platform transfer: completed successfully.
STEP 4 - Configuration upload: verified successfully.
STEP 5 - COMMS restart: recovered as expected.
STEP 6 - TX Modulation: restored, downlink confirmed.
STEP 7 - Final verification: state recorded.
End of contact: 20 s contingency margin unused.

## Slide 7
Summary
All required activities fit the 10-minute window, with a 20 s margin preserved
Contact Plan, flow diagram and script share one consistent time budget (Table 7)
Script validated against 6 independent failure scenarios
Design reflects Open Cosmos operating principles: safety, verification, protected communications
Thank you! Questions?
Anastasia Maria Giannakopoulou · Satellite Flight Operator Challenge Project · August 2026